## Sheet1
Day | Phase | Tasks Completed | Key Deliverables
Day 1 | TTS Laboratory Research, Benchmarking & Custom Zero-Shot Voice Cloning | 1. Sourced and inspected 8 TTS models (Chatterbox Turbo, Fish Speech S2, XTTS-v2, CosyVoice 3, OmniVoice, IndexTTS2, Kokoro-82M, and ElevenLabs baseline). 2. Generated initial comparison metrics (Inference Time, CPU/VRAM usage, Real-Time Factor) and created charts. 3. Upgraded fallback speech engine from robotic Windows SAPI5 to highly natural neural backend (Kokoro-82M). 4. Configured Streamlit thread-safety by wrapping CoInitialize calls for background execution. 5. Integrated F5-TTS flow-matching zero-shot cloning to generate speech in your exact voice using my_voice.wav. 6. Configured imageio-ffmpeg dynamically to bypass system-level FFmpeg path installation errors. 7. Installed CUDA PyTorch to enable GPU acceleration, reducing cloning times from 152s (CPU) down to 5.2s (GPU) on RTX 3060. 8. Created showcase.html, a fully self-contained sharing page with Base64 embedded audio files. | dashboard.py, scripts/speech_synth_helper.py, benchmark_results.csv, showcase.html, voices/my_voice.wav
Day 2 | Local Model Storage, Voice Sample Cleaning, Pronunciation Engine, & UI Enhancements | 1. Integrated Audio8-TTS-Preview-0.6b, a dual autoregressive multilingual zero-shot voice cloning model. 2. Implemented custom transformers class registration mapping in scripts/audio8/ to resolve HuggingFace dynamic package import issues on Windows. 3. Cleaned background noise from user MP3 voice sample using noisereduce, converted to WAV, transcribed with Whisper for naming (Sample.wav), and trimmed to 40.0s. 4. Filtered non-critical Python warnings (Google, Torchaudio, PyTorch) and muted HuggingFace HTTP HEAD connection retries in the console logs. 5. Added interactive Voice Tuning post-processing sliders (Pitch shift, Speed/Tempo stretch, Audio Trimming) using librosa's phase vocoder. 6. Designed the Voice Clone Arena comparison tab, enabling side-by-side prompt synthesis and latency metrics across multiple engines in columns. 7. Createdconfigs/pronunciation_map.json and case-insensitive word boundary replacement pipeline to resolve name pronunciation (like 'Aryan') and acronym spacing. | configs/pronunciation_map.json, scripts/audio8/, voices/Social Media/that_feeling_of_being.wav, .venv/hf_cache/, D:\Saurav\TTS\workspace_history.xlsx
Day 3 | Voice Dataset Organization, GitHub Showcase & HTML Lazy-Loading Architecture | 1. Sourced, cleaned, and organized 10 distinct voice profiles across 8 genres (Announcement, Audiobook, Motivational, Narration, Podcast, Presentation, Social Media, Storytelling). 2. Processed voice samples using DeepFilterNet3, noisereduce, spectral subtraction, 80Hz high-pass filtering, and smooth cosine fade-ins/outs trimmed to <=15s. 3. Created batch synthesis engines (generate_all_model_samples.py & build_new_models_folder.py) generating 90 voice samples across all 9 TTS models. 4. Pushed 90 individual audio samples to GitHub repository (Aryan140314/Text-to-Speech-Models) using automated per-file commits. 5. Re-architected TTS_Voice_Showcase.html to stream audio directly from GitHub raw URLs, reducing HTML size from 46MB down to 52KB for instant browser load times. 6. Implemented interactive filter pills, search bar, and model tab navigation for seamless side-by-side voice comparison. | TTS_Voice_Showcase.html, models_all_voices/, push_to_github_one_by_one.py, build_new_models_folder.py, voices_clean/
Day 4 | Context Overflow Auto-Chunking, Tokenizer Auto-Healing & Structured Output Architecture | 1. Built _chunk_text_for_f5tts() sentence/clause splitter (300-word budget) with audio array concatenation to fix F5-TTS 8,192-token context limit errors. 2. Implemented _clear_hf_model_cache() auto-healing to detect corrupted tokenizer.json files, wipe HF cache, and force clean re-downloads for Audio8. 3. Added proactive multi-model stability guards: Chatterbox word length cap (500 words), Kokoro silent segment filtering (<100 samples), and gTTS network timeout handling. 4. Standardized output folder architecture (folder 1/) organizing 9 model subfolders ([ Model Name ]) with [Genre] VoiceName.wav output formatting. 5. Produced voice_description_and_credits.md detailing voice source links, tone/pitch metrics, WPM pace, and 10,000-credit budget calculations. | scripts/speech_synth_helper.py, D:\Saurav\TTS\1\, voice_description_and_credits.md, workspace_history.xlsx
Day 5 | Complete Legacy Model Deprecation & Zero-Shot Engine Consolidation | 1. Audited repository models and permanently deprecated Audio8-TTS-Preview and Kokoro-82M from codebase, scripts, configs (models_config.json), HTML showcase, and Streamlit menus. 2. Deleted physical legacy model directories (scripts/audio8/, models_all_voices/[ Audio8-TTS-Preview ], models_all_voices/[ Kokoro-82M ]). 3. Re-routed default model synthesis dispatch and fallback chains in speech_synth_helper.py to route through high-fidelity zero-shot cloners (F5-TTS & Chatterbox Turbo). 4. Verified zero-shot voice cloning capabilities across all 7 remaining active models (F5-TTS, Chatterbox Turbo, Fish Speech S2, OmniVoice, CosyVoice 3, XTTS-v2, IndexTTS2). | dashboard.py, scripts/speech_synth_helper.py, configs/models_config.json, TTS_Voice_Showcase.html
Day 6 | Standardized Model Adapter Architecture & Application-Level 2,000-Word Pipeline | 1. Designed and implemented an object-oriented adapter architecture in scripts/tts_adapters.py defining base class TTSModelAdapter and 7 concrete adapters (F5TTSAdapter, ChatterboxAdapter, FishSpeechAdapter, OmniVoiceAdapter, CosyVoiceAdapter, XTTSv2Adapter, IndexTTS2Adapter). 2. Enforced application-level maximum input ceiling (MAX_WORDS = 2000) in dashboard.py with live word/character counters and automatic submit button disabling when limit is exceeded. 3. Implemented IntelligentChunker for sentence-aware (Paragraph -> Sentence -> Clause -> Word) and tokenizer-aware text splitting (~60 words per chunk) to eliminate internal context window overflow. 4. Integrated SpeakerConditioningCache to cache Whisper reference transcripts and speaker embeddings keyed by file path and mtime, avoiding re-extraction overhead. 5. Implemented live CUDA VRAM status reporting and Real-Time Factor (RTF = GenTime / Duration) metrics display in the Streamlit web studio. | scripts/tts_adapters.py, dashboard.py, implementation_plan.md, walkthrough.md
Day 7 | Precision Audio DSP Trimming | 1. Developed precision sample-level audio trimming scripts using soundfile and wave to trim leading silence and custom offsets (0-5s, 0.05s, 0.5s, 0.3s) from long-form audio files. 2. Preserved exact 24,000 Hz sample rate and created automatic original audio backups (..._orig.wav) before modification. 3. Automated per-file Git commit workflow using scripts/push_all_changes_one_by_one.py and scripts/push_remaining_one_by_one.py to stage, commit, and push 53+ items individually to GitHub (Aryan140314/Text-to-Speech-Models). 4. Verified clean working tree status on origin/main. | outputs/omnivoice/, scripts/push_all_changes_one_by_one.py, scripts/push_remaining_one_by_one.py
Day 8 | Repository-Level Architecture Audit & 52-Section Master Technical Documentation | 1. Performed a non-destructive repository-level code inspection tracing imports, function calls, model wrappers, preprocessing pipelines, and hardware execution paths across all workspace directories. 2. Authored a comprehensive 52-section technical architecture document (project_architecture_analysis.md) covering Executive Summary, Data Flow, Pipeline Connection Map, Zero-Shot Voice Cloning Analysis, GPU/CUDA Pipeline, and One-Page Project Summary. 3. Documented real empirical benchmark measurements across all 7 TTS model adapters running on CUDA GPU (RTX 3060 12GB). 4. Updated configs/models_config.json and synchronized workspace history and documentation with GitHub main branch. | project_architecture_analysis.md, workspace_history.xlsx, configs/models_config.json
Day 9 | Desktop UI Transformation — Electron + React + TypeScript + Local FastAPI Backend | 1. Architected and created decoupled backend/ and ui/ workspace directories. 2. Built backend/app/core/paths.py resolving user data to %LOCALAPPDATA%\TTS-Studio\ with local portable dev fallback. 3. Implemented local FastAPI REST backend service (backend/app/main.py) with dynamic port binding (--port) and routes for system hardware, models, voices, generation, and benchmarking. 4. Migrated existing 7-model zero-shot synthesis engine (tts_adapters.py, speech_synth_helper.py, clean_voice_dataset.py, benchmark_engine.py) into backend/tts/. 5. Implemented hardware_service.py dynamically detecting CPU, RAM, NVIDIA CUDA GPU, VRAM, and PyTorch capability. 6. Developed Electron main process (ui/electron/main.ts), secure preload bridge (preload.ts), and backendManager.ts spawning Python backend on free dynamic port. 7. Built modern React + TypeScript web studio UI (ui/src/) with Tailwind CSS, shadcn/ui styling, Framer Motion, Zustand state stores, and React Query clients. 8. Configured standalone packaging specs: backend/build_backend.spec (PyInstaller) and ui/electron-builder.yml (NSIS installer TTS-Studio-Setup.exe). | backend/app/main.py, ui/electron/main.ts, ui/src/app/App.tsx, backend/build_backend.spec, ui/electron-builder.yml